Start up Plan for

the Regional Secretariat for Parliamentary Cooperation in SEE

- Transfer the existing know-how in the field of Parliamentary Cooperation from SP to the Regional Secretariat for Parliamentary Cooperation

  - Fact finding mission to Brussels and/or

  - Short or long term secondment of an established SP expert to Sofia

  - Key contacts within the SEECP National Parliaments

  - Key contacts within the SP Parliamentary Troika as well as other partnering formats

  - Key donor contacts

  - Technology of putting projects together

  - Technology of raising donor money

  - Technology of assuming donor money (to be custom tailored)

  - Technology of monitoring and assessing project results (to be created if it does not exist)

  - Financial reporting and book keeping standards and requirements

- Draft Terms of Reference for the Regional Secretariat for Parliamentary Cooperation

- Draft an invitation to the SEECP National Parliaments to second experts to Sofia by the end of 2007

- Define the future role and involvement of the European Parliament, Parliamentary Assembly of the Council of Europe and the Parliamentary Assembly of OSCE

- Conduct a thorough needs assessment and identify  priority areas for action

- Draft preliminary Parliamentary Programme 2008 with the assistance of SP PCTF

- Prepare draft budgetary projections 2008/2009 with the assistance of the SP

- Propose initial scheme for financial commitments by the Parliaments in the Region as percentage of the programmatic budget based on a formula for fair burden distribution

- Initiate consultations with existing and potential new donors to identify possible programmatic budget inflows for the period 2008-2009

- Identify possible projects and create a project data base

- Prepare a project proposal for creating an internet portal for SEE Parliamentary Cooperation

- Identify possible trainings for the already appointed staff

- Draft a MoU institutionalizing the parliamentary cooperation in the region and outlining region’s responsibilities and commitments as well as partner’s involvement

- MoU and the Terms of Reference for the Secretariat to be endorsed by the SEECP Speakers of Parliaments at the meeting for the official launch of the Secretariat

- Prepare the meeting and official ceremony for the launch of the Regional Secretariat